## Sheet1
No. | Risk | Impact | Likely | Impact-Level | Response plan
R1 | Project delay | Unable to develop our website, deploy on time. | EH | M | Carefully plan, make a good bug triage and test carefully.
R2 | Not meet to the quality standards. | Unable to deliver, repeating development and cause project delay | M | EH | Software Quality Assurance, test during the coding and make sure there’s no bug.
R3 | Requirements change | Repeating development, cost increase and cause project delay | H | H | Analysis requirements carefully, use incremental development, keep contacting with stakeholders
R4 | Over budget | Unable to deliver the project, must spend time to raise more money | L | M | Estimate cost carefully and control the budget real time.
R5 | Staff absence or changes during the development | May cause project delay and low quality work and increase the cost | EL | M | Estimate the workload carefully, assign work reasonably and make an efficient team management.
R6 | Not meet the functional requirements | Must do additional developments and cause the project delay | EL | EH | Design the project carefully to ensure the design of each functional point is completed.